## Slide 1: Optimal Option Investment Strategy
Sponsor: Dr. K.C. Chang
Tony Chen
Ehsan Esmaeilzadeh
Ali Jarvandi
Ning Lin
Ryan O’Neil
Spring 2010

## Slide 2: Outline
Background
Problem Statement
Statement of Need
Project Scope
Requirements
Assumptions
Approach
Optimal Fraction Analysis
Simulation and Results
Work Breakdown Structure
Tasks Status Summary
Project Schedule
Earned Value Management

## Slide 3: Background

## Slide 4: Background
ECON 101:
Futures contract – An mutual agreement to trade a commodity in the future between two traders
Expiration date – The date the futures contract is effective
Strike price – Price at which the commodities are traded (usually market price for standard futures contract)
Positions – Long (buyer) and short (seller)

## Slide 5: Background
Option – A conditional futures contract with a pre specified strike price. Option buyer gets right to exercise contract
  American
  European
Premium – Price option buyer pays to have right to exercise
Two general types: call (right to buy) and put (right to sell)
“In the money” – An option would have positive return if exercised at this instant

## Slide 6: Background
Long Position (buyer) – Theoretically limitless
  Call: Commodity price greater than strike price
  Put: Commodity price less than strike price
Short Position (seller) – Maximum is the premium from selling option. Gets full amount if option is not exercised
Stop Loss – Maximum amount seller is willing to lose. Executed by buying back the same option

## Slide 7: Background
Short Strangle Strategy:
  Simultaneously selling a call and a put with the same expiration date
Strike prices for each option can be different
Typically call strike price is greater than commodity price and put strike price is less than commodity price (at options writing)
Greatest payoff when commodity price at expiration date is between strike prices
Best used on a commodity with low rate of volatility

## Slide 8: Background

## Slide 9: Optimal Option Investment Strategy Team
Our goal is:
  to provide policy recommendations for the option sellers to maximize profit and minimize risk of loss
  to determine the optimal fraction for investment
  to develop graphical user interface to plot equity curves of the selected strategies
We help the option seller to know when and at what price to trade the option
6 years of real historical data on option prices, instead of estimated prices

## Slide 10: Problem Statement
Investors can potentially earn huge profits by trading assets
Options allow investors to leverage current assets to trade in greater quantities
Most investors trade on speculation and attempt to predict the market
It is difficult to find an optimal investment strategy that balances high returns on investment with low risk of catastrophic loss

## Slide 11: Statement of Need
There is a need for a solid well-documented analysis to provide investment strategies for investors with different characteristics and help them in selecting the best strategy for a maximum benefit
There is also a need for a computer based application analyzing historical market data and providing feedback to users

## Slide 12: Concept of Operations

## Slide 13: Project Scope
Range of data: 2004-2009
Underlying asset is S&P 500 future index
Short strangle strategies only
Strike prices ±$50 from asset price at increments of 5
Stop loss from 5 to 45 at increments of 5

## Slide 14: Assumptions
Assumptions:
  American options only
  Use of calendar days instead of trading days
  Strategies, missing data points more than 50% are ignored
  Only make trades at the end of a trading day
  Do not consider interest rate
  Do not simulate trading commission or slippage
  Use SP500 index prices rather than SP500 futures as the underlying asset
  Estimate difference of strike prices and asset price by $5 increments, not scaled to index prices.

## Slide 15: Requirements
The analysis shall provide recommendations on investment policies
  Consider expected return on investment and risk of ruin in providing recommendations
  Provide different sets of recommendations based on the level of risk acceptable by an investor

## Slide 16: Requirements
The software system shall provide the expected return and risk for any given strategy
  Take input from users using a graphic user interface
  Present the return on investment (equity curve) as a function of time

## Slide 17: Approach
Research on the topic
  Relevant papers
  Previous team’s work
Parse the historical data
Develop the simulation model
Validate & analyze results
Revise the model as needed
Determine optimal strategies and optimal fraction for investment
Develop Graphical User Interface

## Slide 18: Methodology

## Slide 19
Optimal f Allocation
Definition
f is a fraction of equity that is invested at options writing date
We write options contracts such that the margin requirement equals f percent of equity.

## Slide 20: Optimal f Allocation
1. Setup initial amount C = $1,000,000;
2. Let f = the fraction of money we invest in the market;
3. Let L = abs (the biggest point loss in our trades);
4. Let Margin = $5,000
5. Let P = the points we earn or lose
For Strategy 1 to Strategy n
For f = 0.05:0.05:1 (this is MATLAB format which means 0.05 0.10 0.15...0.95 1)
NewMoney = C;
For Trade 1 to Trade 60
B = NewMoney *f ;
NumberOfContract = B/max (L*50, Margin);
NewMoney = NumberOfContract*P*50+NewMoney;
TWR = NewMoney/C (TWR should be displayed)
End
End
End

## Slide 21: Risk of Ruin
Definition: Ruin is a state losing a significant portion (often set at 50%) of your original equity.
Computation methods:
  Vince formula
  Monte Carlo simulation
  Futures formula

## Slide 22: Risk of Ruin
Algorithm:
  R = e^((-2*a/d)*(ln(1-z)/ln(1-d)))
  Where a = mean rate of return
  d = standard deviation of the rate
  z = how we define ruin. Here is 50%.
  Sharpe ratio = a / d
Risk of Ruin Example

## Slide 23: Simulation and Results

## Slide 24: Simulation

## Slide 25: Results
Determination of most profitable investment strategy with the following attributes:
  Strike price
  Put & call prices
  Premium
  Monthly profit over the investment period
  Stop loss
  Optimal f
  Final TWR
  Minimum TWR

## Slide 26: Tasks & Schedule

## Slide 27: Work Breakdown Structure (WBS)

## Slide 28: Project Schedule (GANTT)

## Slide 29: Earned Value Management (EVM)

## Slide 30: Cost & Schedule Performance Index

## Slide 31: Questions

## Slide 32: Background for Optimal f Allocation
Kelly formula:
f = (b*p – q)/b
f* is the fraction of the current bankroll to wager
b is the net odds received on the wager (that is, odds are usually quoted as "b to 1")
p is the probability of winning
q is the probability of losing, which is 1 − p

## Slide 33: Validation
Two assumptions of this formula:
1. Winning and losing per bet is constant
2. Total bet is large enough
in our case
1. the return from each trade is different
2. total trade is limited
So, we cannot this formula

## Slide 34: How to make investment
Introduced by Vince in his book The New Money Management, we should use:
f$ = abs (biggest losing trade)/optimal f
Where f$ means how much a contract worth

## Slide 35: Operational Scenario

## Slide 36: Option Payoff

## Slide 37: References
Kolb, Robert (1995), Understanding Options. New York, John Wiley & Sons, Inc.