## Slide 1: SYST699 – Spec Innovations
Innoslate™ System Engineering Management Software Tool Test & Analysis

## Slide 2: Agenda
Background - Innoslate
Problem Definition
Project Objectives
Project Approach
Project Status
Project Schedule

## Slide 3: Background – Innoslate™
Innoslate™ Systems Engineering Tool
  Tool was developed as the aggregation of several systems engineering tools and concepts that have been utilized for the past 25 years.
  Cloud-based web application developed specifically for systems engineers to encompass activities related to the full systems lifecycle.
  Includes capabilities related to requirements management, collaboration, system modeling, reporting, and discrete event simulation.

## Slide 4: Problem Definition
  Software product development is very new to SPEC Innovations necessitating a critical review and analysis of the Innoslate™ tool to provide independent feedback and recommendations.
  SPEC Innovations’ primary need is an evaluation of the tool’s usability and the functionality to measure its ability to assist system engineers in doing their job.

## Slide 5: Project Objectives
  Testing and critical/comparative evaluation of the capabilities offered by Innoslate™.
  Compile and detail test results, feature comparisons, recommendations, and trade study analysis as part of a report to the sponsor.
  Deliver the final project report and present project and finding to the sponsor and GMU faculty.

## Slide 6: Project Approach [1]
  Based on feedback the scope was defined to utilize the final report for a project from SYST513, Meeting and Event Planning System (MEEPAS).
          MEEPAS is a Meeting and Event Planning Assistant System
            Intended for increasing efficiency and reducing technical difficulties for requesting, scheduling, executing, and monitoring meetings

## Slide 7: Project Approach [2]
  Project activities during MEEPAS project included: Development of CONOPs, System Requirements, as well as measures of effectiveness and performance.
  Test cases will be developed based on the system development lifecycle phases that are addressed in the final report; concept of operations (CONOPS), requirements elicitation and management, system architecture design and modeling.

## Slide 8
Project Approach [3]
  The tool will also be utilized to capture the project requirements, test cases, and test execution results.
  Mozilla Firefox and Google Chrome web browsers will be utilized to conduct the system testing to provide broader usability feedback. (Internet Explorer is not supported currently)
  Provide feedback and functionality gaps to SPEC Innovations via the InnoSlate feature tracker tool.

## Slide 9: Project Status [1]
  Hold kick-off meeting with sponsor - Competed; bi-weekly progress meetings established.
  Identify scope and methodology – Completed; identified project and stage of the SELC to focus tests for Innoslate.
  Components selected within Innoslate to focus testing on:
  Database functions- storing of Assets, Artifacts, etc.
  Requirement Gathering functions- Our project requirements as well as requirements of the selected MEEPAS project.

## Slide 10: Project Status [2]
  Report Generation functions: Based on inputted objects into the database.
  Document Analyzer functions: Automated versus Manual parsing of inputted documents.
  Identify and document user requirements – In progress
  Develop Project Status Report – Target completion: 10/11/2012
  Develop test plans and testing requirements - In progress; target completion: 10/11/2012

## Slide 11: Project Status [3]
  Conduct tests and evaluation – Target completion: 11/8/2012
  Develop Final Presentation – Target completion: 12/6/2012
  Develop Final Report – Target completion: 11/29/2012

## Slide 12: Schedule [1]
UID | Activity | Start Date | Finish Date | Contact
1 | SEM Analysis Kick-Off | 8/30/2012 | 9/13/2012 | Ceely/Matthews/Stevenson/Woldie
1.1 | Hold Initial Meeting with Sponsor | 9/10/2012 | 9/10/2012 | Ceely/Matthews/Stevenson/Woldie
1.2 | Problem Definition Presentation | 8/30/2012 | 9/13/2012 | Ceely/Matthews/Stevenson/Woldie
1.2.1 | Develop Presentation | 8/30/2012 | 9/12/2012 | Ceely
1.2.2 | Present Presentation | 9/13/2012 | 9/13/2012 | Ceely/Matthews/Stevenson/Woldie

## Slide 13: Schedule [2]
UID | Activity | Start Date | Finish Date | Contact
2 | SEM Project Scope and Methodology | 9/14/2012 | 10/14/2012 | Ceely/Matthews/Stevenson/Woldie
2.1 | Analyze Past Projects for Selection | 9/14/2012 | 9/21/2012 | Ceely/Matthews/Stevenson/Woldie
2.2 | Select Past Project | 9/22/2012 | 9/23/2012 | Ceely/Matthews/Stevenson/Woldie
2.3 | Scope SELC Phase | 9/22/2012 | 9/23/2012 | Ceely/Matthews/Stevenson/Woldie
2.4 | Requirements | 10/1/2012 | 10/14/2012 | Matthews
2.4.1 | Develop Requirements | 10/1/2012 | 10/7/2012 | Matthews
2.4.2 | Review Requirements | 10/7/2012 | 10/9/2012 | Ceely/Matthews/Stevenson/Woldie

## Slide 14: Schedule [3]
UID | Activity | Start Date | Finish Date | Contact
2.4.3 | Incorporate Inputs | 10/10/2012 | 10/13/2012 | Matthews
2.4.4 | Submit Requirements | 10/14/2012 | 10/14/2012 | Matthews
2.5 | Approach Presentation | 9/24/2012 | 10/4/2012 | Ceely/Matthews/Stevenson/Woldie
2.5.1 | Develop Approach Presentation | 9/24/2012 | 10/1/2012 | Stevenson
2.5.2 | Present Approach Presentation | 10/4/2012 | 10/4/2012 | Ceely/Matthews/Stevenson/Woldie

## Slide 15
UID | Activity | Start Date | Finish Date | Contact
3 | Test and Evaluation of Innoslate | 10/4/2012 | 11/8/2012 | Ceely/Matthews/Stevenson/Woldie
3.1 | Develop Test Plans | 10/4/2012 | 10/11/2012 | Woldie
3.1.1 | Requirements Test Plan | 10/4/2012 | 10/11/2012 | Woldie
3.1.2 | Design Test Plan | 10/4/2012 | 10/11/2012 | Woldie
3.2 | Conduct Test | 10/12/2012 | 10/26/2012 | Ceely/Matthews/Stevenson/Woldie
3.2.1 | Requirements Test | 10/12/2012 | 10/19/2012 | Ceely/Matthews/Stevenson/Woldie
3.2.2 | Design Test | 10/20/2012 | 10/26/2012 | Ceely/Matthews/Stevenson/Woldie
3.3 | Evaluate Test Results | 10/26/2012 | 11/8/2012 | Ceely/Matthews/Stevenson/Woldie
Schedule [4]

## Slide 16: Schedule [5]
UID | Activity | Start Date | Finish Date | Contact
4 | Final Presentation | 10/4/2012 | 12/6/2012 | Ceely/Matthews/Stevenson/Woldie
4.1 | Develop Final Presentation | 10/4/2012 | 10/31/2012 | Stevenson
4.2 | Submit Draft Final Presentation | 11/1/2012 | 11/1/2012 | Stevenson
4.3 | Incorporate Presentation Feedback | 11/2/2012 | 11/26/2012 | Stevenson
4.4 | Final Presentation Rehearsal | 11/29/2012 | 11/29/2012 | Ceely/Matthews/ Stevenson/Woldie
4.5 | Final Presentation – Faculty | 12/6/2012 | 12/6/2012 | Ceely/Matthews/ Stevenson/Woldie
5 | Final Report | 10/11/2012 | 11/29/2012 | Ceely/Matthews/ Stevenson/Woldie
5.1 | Develop Phase I (Initial) of Final Report | 10/11/2012 | 11/15/2012 | Ceely

## Slide 17: Schedule [6]
UID | Activity | Start Date | Finish Date | Contact
5.2 | Incorporate Input | 11/16/2012 | 11/19/2012 | Ceely
5.3 | Develop Phase II (Final) of Final Report | 11/08/2012 | 11/25/2012 | Ceely/Matthews/ Stevenson/Woldie
5.4 | Tech Edit Final Report | 11/25/2012 | 11/28/2012 | Stevenson
5.5 | Submit Final Report | 11/29/2012 | 11/29/2012 | Stevenson
6 | Administrative Presentations and Reports | 10/4/2012 | 10/18/2012 | Ceely/Matthews/Stevenson/Woldie
6.1 | Project Status Report | 10/4/2012 | 10/11/2012 | Stevenson
6.2 | In Progress Review Presentation | 10/11/2012 | 10/18/2012 | Ceely/Matthews/Stevenson/Woldie

## Slide 18: Questions