## BI Process Improvement Rollout
Task Name | Assigned To | Start Date | End Date | Cost | % Complete | Comments | Predecessors | Duration
PHASE 1 |  | 2012-06-01 | 2013-09-17 |  |  |  |  | 338
Standardization |  | 2012-06-01 | 2012-06-01 |  |  |  |  | 1
Response Matching Wait Time |  | 2012-06-01 | 2012-06-01 |  |  |  |  | 1
Communicate BI Can't Guarantee Match If Not Met |  | 2012-06-01 | 2012-06-01 |  |  |  |  | 1
Response Feedback Wait Time |  | 2012-06-01 | 2012-06-01 |  |  |  |  | 1
Task Management |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Asana Checklist Templates |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Prepare Current Procedures Checklist |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Donation Drives Checklist |  | 2012-06-04 | 2012-06-06 |  |  |  |  | 3
Blood Drives Checklist |  | 2012-06-04 | 2012-06-06 |  |  |  |  | 3
Community Events Checklist |  | 2012-06-04 | 2012-06-06 |  |  |  |  | 3
In-Office Events Checklist |  | 2012-06-06 | 2012-06-08 |  |  |  |  | 3
Corporate Events Checklist |  | 2012-06-06 | 2012-06-08 |  |  |  |  | 3
One-Off Donations Checklist |  | 2012-06-06 | 2012-06-08 |  |  |  |  | 3
Assign Tasks and Due Dates |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Sync Checklist for Outlook Reminders |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Take Checklist to Event (Print or Smartphone) |  | 2012-06-04 | 2012-06-08 |  |  |  |  | 5
Salesforce |  | 2012-06-11 | 2012-06-12 |  |  |  |  | 2
Install Salesforce for Outlook |  | 2012-06-11 | 2012-06-12 |  |  |  |  | 2
Vertical Response |  | 2012-06-12 | 2012-06-14 |  |  |  |  | 3
Demo: Using Vertical Response for Salesforce |  | 2012-06-12 | 2012-06-13 |  |  |  |  | 2
Install Vertical Response for Salesforce |  | 2012-06-12 | 2012-06-13 |  |  |  |  | 2
Send Test Email |  | 2012-06-12 | 2012-06-12 |  |  |  |  | 1
Create and Send Monthly Email |  | 2012-06-13 | 2012-06-13 |  |  |  |  | 1
Watch Update Salesforce Statistics Video |  | 2012-06-13 | 2012-06-13 |  |  |  |  | 1
Update Survey Statistics in Salesforce Through Vertical Response |  | 2012-06-13 | 2012-06-14 |  |  |  |  | 2
Donation Drives |  | 2012-06-15 | 2012-06-15 |  |  |  |  | 1
Use Route Optimization Software |  | 2012-06-15 | 2012-06-15 |  |  |  |  | 1
Email Outlook Calendar Task to PM for Donation Boxes |  | 2012-06-15 | 2012-06-15 |  |  |  |  | 1
One-Off Donations |  | 2012-06-18 | 2012-06-20 |  |  |  |  | 3
Partner with Boston Restore/Furniture Trust for Pick-up |  | 2012-06-18 | 2012-06-20 |  |  |  |  | 3
In-Office Events |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Recruit Office Volunteer(s) for Help |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Train Ambassador and Volunteer(s) |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Provide Printouts of Step-By-Step Instructions |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Backup Activities |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Prepare Set of Generic Backup Activities that are Always Available |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Community Events |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Corporate Events |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
In-Office Events |  | 2012-06-18 | 2012-06-22 |  |  |  |  | 5
Developers |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Need Developer with Salesforce Experience to Implement Salesforce Customization in Phase 2 |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Volunteer: Catch a Fire |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Cheap Overseas: Elance |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Feedback |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Survey NPPs for Web Portal Interest |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Create Ambassadors Online Surveys |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Create Volunteers Online Surveys |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Email Ambassadors Link for Survey Post-Event |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Email Volunteers Link for Survey Post-Event |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Use Survey Report to Input Feedback in Salesforce |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Donation Drives |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Get Volunteer Intern Help with Pickups |  | 2012-06-25 | 2012-06-29 |  |  |  |  | 5
Quarterly Calendar |  | 2012-10-15 | 2013-09-17 |  |  |  |  | 242
Publish Jan - Mar Calendar Nov 15 |  | 2012-10-15 | 2012-11-15 |  |  |  |  | 24
Publish Apr - Jun Calendar Feb 15 |  | 2013-01-15 | 2013-02-15 |  |  |  |  | 24
Publish Jul - Sep Calendar May 15 |  | 2013-08-15 | 2013-09-17 |  |  |  |  | 24
Publish Oct - Dec Calendar Aug 15 |  | 2012-12-14 | 2013-01-16 |  |  |  |  | 24
PHASE 2 (Developer Required) |  | 2012-07-02 | 2013-01-31 |  |  |  |  | 154
Website Bugs |  | 2012-07-02 | 2012-07-06 |  |  |  |  | 5
Fix "Call to Action" Button Sub-heading Options Under "Get Involved" |  | 2012-07-02 | 2012-07-04 |  |  |  |  | 3
Fix Site Map with Section "Dessault Systemes DOS" and "Community Engagement Survey" Spelling |  | 2012-07-02 | 2012-07-06 |  |  |  |  | 5
General Re-design |  | 2012-07-09 | 2012-07-20 |  |  |  |  | 10
Appropriate Attire Info |  | 2012-07-09 | 2012-07-13 |  |  |  |  | 5
Add to Event Page |  | 2012-07-09 | 2012-07-13 |  |  |  |  | 5
Add to Sign-up |  | 2012-07-09 | 2012-07-13 |  |  |  |  | 5
Add to Reminder Emails |  | 2012-07-09 | 2012-07-13 |  |  |  |  | 5
Upcoming Events Page |  | 2012-07-09 | 2012-07-20 |  |  |  |  | 10
Contact Info and How to Participate |  | 2012-07-09 | 2012-07-09 |  |  |  |  | 1
Clearly Identify and Separate Time, Date, Location, Event Description |  | 2012-07-09 | 2012-07-09 |  |  |  |  | 1
Sign-up Form Open by Default on Event Details Page |  | 2012-07-10 | 2012-07-10 |  |  |  |  | 1
Select Events by Geographic Region |  | 2012-07-11 | 2012-07-13 |  |  |  |  | 3
Month-by-Month Calendar of Events |  | 2012-07-16 | 2012-07-20 |  |  |  |  | 5
Online Sign-up |  | 2012-07-16 | 2012-10-08 |  |  |  |  | 61
Donation Drives and Community Events Sign-up |  | 2012-07-16 | 2012-09-05 |  |  |  |  | 38
Online Sign-up Form |  | 2012-07-16 | 2012-07-17 |  |  |  |  | 2
Automatic Email Confirmation with Cancel Link |  | 2012-07-17 | 2012-07-18 |  |  |  |  | 2
Provide Minimum Number of Sign-ups Needed |  | 2012-07-19 | 2012-07-20 |  |  |  |  | 2
Counter (starting at 5) to Display when Event About to Fill Up |  | 2012-07-23 | 2012-08-10 |  |  |  |  | 15
Deactive Sign-up Once Event Filled |  | 2012-08-13 | 2012-08-31 |  |  |  |  | 15
Automatic 48 hr Reminder Email to Confirm/Cancel |  | 2012-09-03 | 2012-09-04 |  |  |  |  | 2
Automatic Email Post-event with Survey Links |  | 2012-09-05 | 2012-09-05 |  |  |  |  | 1
Blood Drives Sign-up |  | 2012-09-05 | 2012-10-08 |  |  |  |  | 24
Select Blood Drive Appointment Time During Sign-up |  | 2012-09-05 | 2012-10-03 |  |  |  |  | 21
Contact Preference Field for Appointment Reminder |  | 2012-10-03 | 2012-10-03 |  |  |  |  | 1
Automatic Email Confirmation |  | 2012-10-04 | 2012-10-04 |  |  |  |  | 1
Link in Automatic Email to Cancel or Change Appointment |  | 2012-10-05 | 2012-10-05 |  |  |  |  | 1
Internal Email Notification of Changes/Cancellations |  | 2012-10-08 | 2012-10-08 |  |  |  |  | 1
Automatic 48 hr Reminder Email to Confirm/Cancel |  | 2012-10-08 | 2012-10-08 |  |  |  |  | 1
Email Event Leader if Contact Preference is Phone |  | 2012-10-08 | 2012-10-08 |  |  |  |  | 1
Email Signee if Contact Preference is Email |  | 2012-10-08 | 2012-10-08 |  |  |  |  | 1
Website Portal |  | 2012-10-15 | 2012-12-31 |  |  |  |  | 56
Affiliates Website Portal (Ambassadors, Building Contacts) |  | 2012-10-15 | 2012-12-14 |  |  |  |  | 45
Required Login |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
"Remember Password" Option to Bypass Login |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Published Calendars and Flyers |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Updates and Generate Automatic Email with Updates |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Event Feedback Reports |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
In-Office Events Sign-up |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Link for Ambassador to Email Employees for Online Sign-up |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Corporate Events Sign-up |  | 2012-10-22 | 2012-12-14 |  |  |  |  | 40
Event Request Form for Buildings |  | 2012-10-22 | 2012-11-02 |  |  |  |  | 10
Building Fills Out Form to Post Event Request with Criteria |  | 2012-10-22 | 2012-11-02 |  |  |  |  | 10
Automatic Email to Building and BI that Event Request Posted |  | 2012-12-03 | 2012-12-07 |  |  |  |  | 5
Automatic Email to NPPs with Matching Criteria About Event Request |  | 2012-12-03 | 2012-12-07 |  |  |  |  | 5
Event Request Displays on NPP Website Portal |  | 2012-12-10 | 2012-12-14 |  |  |  |  | 5
NPP Website Portal |  | 2012-10-15 | 2012-12-31 |  |  |  |  | 56
Required Login |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
"Remember Password" Option to Bypass Login |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Published Calendars and Flyers |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Updates and Generate Automatic Email with Updates |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Post Event Feedback Reports |  | 2012-10-15 | 2012-10-19 |  |  |  |  | 5
Corporate Events Sign-up |  | 2012-10-22 | 2012-12-31 |  |  |  |  | 51
NPPs Fill Out Criteria During Account Setup to be Used in Criteria Matching |  | 2012-10-22 | 2012-11-02 |  |  |  |  | 10
Create Criteria Matching Mechanism |  | 2012-11-05 | 2012-11-30 |  |  |  |  | 20
"We Are Interested" Button for NPP to Express Interest in Event |  | 2012-12-17 | 2012-12-21 |  |  |  |  | 5
Automatic Email to NPP and BI that NPP Interested in Event |  | 2012-12-24 | 2012-12-31 |  |  |  |  | 6
Automatic Email to Building with NPP Info and Interest in Event |  | 2012-12-24 | 2012-12-31 |  |  |  |  | 6
Salesforce Customization |  | 2013-01-01 | 2013-01-31 |  |  |  |  | 23
Pull Participant Info from Automatic Sign-up Email to Automatically Populate Salesforce Fields |  | 2013-01-01 | 2013-01-31 |  |  |  |  | 23
Donation Drives |  | 2013-01-01 | 2013-01-31 |  |  |  |  | 23
Blood Drives |  | 2013-01-01 | 2013-01-01 |  |  |  |  | 1
Community Events |  | 2013-01-01 | 2013-01-01 |  |  |  |  | 1
In-Office Events |  | 2013-01-01 | 2013-01-01 |  |  |  |  | 1
Corporate Events |  | 2013-01-01 | 2013-01-01 |  |  |  |  | 1